# Parking API — Project Documentation

Real-time Parking Availability Backend

# 1. Project Overview

A real-time parking availability app designed to show users where spots are free. The solution covers both Web and Mobile platforms and uses a mix of IoT sensors, cameras, and manual override to detect spot availability.

# 2. High-Level Architecture

Data Sources: IoT Sensors, Cameras / Computer Vision, Manual Input

Backend API (Node.js + Express): WebSocket real-time push, REST API, Auth & admin panel, PostgreSQL + Redis

Frontend: Web App (React / Next.js) and Mobile App (React Native) showing a live map of spot availability

# 3. Recommended Tech Stack

| Layer | Technology |
| --- | --- |
| Runtime | Node.js (Express / Fastify) |
| Database | PostgreSQL + Redis |
| Real-time | WebSockets (Socket.io) |
| Sensor Input | MQTT broker (Mosquitto) |
| Auth | JWT + bcrypt |
| API Docs | Swagger / OpenAPI |
| Deployment | Docker + Railway / Render / AWS |

# 4. 15-Day Build Plan

## Week 1 — Foundation (Days 1–5)

| Day | Task | Hours/Day |
| --- | --- | --- |
| 1 | Project setup, DB schema design, environment config | 3-4 hrs |
| 2 | Auth module (JWT, login, register, roles) | 3-4 hrs |
| 3 | Parking lot CRUD (create, list, update, delete) | 3-4 hrs |
| 4 | Parking spot CRUD + status management | 3-4 hrs |
| 5 | Buffer / catch-up / review and testing | 2-3 hrs |

## Week 2 — Core Features (Days 6-10)

| Day | Task | Hours/Day |
| --- | --- | --- |
| 6 | Real-time WebSocket layer (spot status push) | 4-5 hrs |
| 7 | Sensor/camera data ingestion endpoint (MQTT or HTTP) | 3-4 hrs |
| 8 | Manual override API + admin controls | 3 hrs |
| 9 | Availability query API (filter by lot, zone, type) | 3 hrs |
| 10 | Buffer / integration testing | 2-3 hrs |

## Week 3 — Polish (Days 11-15)

| Day | Task | Hours/Day |
| --- | --- | --- |
| 11 | Booking/reservation module | 3-4 hrs |
| 12 | History and analytics endpoints | 3 hrs |
| 13 | Rate limiting, error handling, validation hardening | 3 hrs |
| 14 | API documentation (Swagger/OpenAPI) | 2-3 hrs |
| 15 | Final testing, cleanup, deployment-ready | 3 hrs |

# 5. Database Schema

The following tables are created by schema.sql and managed via the migration runner:

| Table | Description |
| --- | --- |
| users | Admins, operators, and viewers with roles and hashed passwords |
| parking_lots | Physical parking locations with address, coordinates, and capacity |
| parking_zones | Sections within a lot (e.g. Floor 1, Zone A) with spot counts |
| parking_spots | Individual spots with real-time status, type, and sensor ID |
| spot_history | Full audit log of every status change with source and timestamp |

# 6. Day 1 — Files Created

The following files were scaffolded on Day 1:

| File | Purpose |
| --- | --- |
| package.json | Project and all dependencies |
| .env.example | Environment variable template (DB, JWT, ports) |
| .gitignore | Ignores node_modules, .env, and logs |
| src/index.js | Server entry point — starts HTTP and WebSocket servers |
| src/app.js | Express app — registers middleware, routes, error handlers |
| src/config/db.js | PostgreSQL connection pool |
| src/config/migrate.js | DB migration runner — executes schema.sql |
| src/utils/logger.js | Winston structured logger |
| src/services/socketService.js | Socket.io initializer and spot update broadcaster |
| src/routes/auth.js | Auth route stubs (fully implemented Day 2) |
| src/routes/lots.js | Parking lots route stubs (fully implemented Day 3) |
| src/routes/spots.js | Parking spots route stubs (fully implemented Day 4) |
| schema.sql | Full DB schema — 5 tables, indexes, auto-update triggers |
| docker-compose.yml | Spins up PostgreSQL and Redis locally |
| README.md | Project docs with getting started guide and build progress |

# 7. Getting Started (Local Setup)

## Step 1 — Install dependencies

npm install

## Step 2 — Configure environment

Copy .env.example to .env and fill in your PostgreSQL credentials and JWT secret.

## Step 3 — Start local database

docker-compose up -d

## Step 4 — Run DB migration

npm run migrate

## Step 5 — Start the server

npm run dev

The API will be available at http://localhost:3000 and a health check endpoint at http://localhost:3000/health.